## Summary
KAUST SECURITY FENCE PROJECT | [7 empty] | KAUST SECURITY FENCE PROJECT
PMCC-04B | [7 empty] | PMCC-04B
• CRASH RATED WALL (TYPE K12) (STA. 4+150 to 14+530) • ISLAND PRECAST WALL (STA.14+530 to 14+834) • PATROL ROAD & 10 METER POLE LIGHTING (STA. 4+150 to 14+460) • WADI KHULAIS CULVERT | [7 empty] | • CRASH RATED WALL (TYPE K12) (STA. 4+150 to 14+530) • ISLAND PRECAST WALL (STA.14+530 to 14+834) • PATROL ROAD & 10 METER POLE LIGHTING (STA. 4+150 to 14+460) • WADI KHULAIS CULVERT
KAUST & CX team | [7 empty] | KAUST | KAUST & CX team
|  | Total |  | Closed |  | Remaining |  |  | Discipline | Total |  | Closed |  | Remaining |  | Discipline | Total |  | Closed
| Discipline | YES | NO | YES | NO | YES | NO |  |  | Y | N | YES | NO | YES | NO |  | Y | N | YES | NO
| Civil | 35 | 41 | 35 | 40 | 0 | 1 |  | Civil | 35 | 41 | 35 | 40 | 0 | 1 | Security | 13 | 0 | 13 | 0
| Electrical | 18 | 31 | 18 | 4 | 0 | 27 |  | Electrical | 18 | 31 | 18 | 4 | 0 | 27 | Electrical | 18 | 31 | 18 | 4
| Security Sys | 13 |  | 13 |  | 0 | 0 |  | Security Sys | 13 | 0 | 13 | 0 | 0 | 0 | Documentation | 0 | 1 | 0 | 0
| MEP | 1 |  | 1 |  | 0 |  |  | MEP | 1 | 0 | 1 | 0 | 0 | 0 | Civil | 35 | 40 | 35 | 40
| Total | 67 | 72 | 67 | 44 | 0 | 28 |  | TOTAL | 67 | 72 | 67 | 44 | 0 | 28 | MEP | 1 | 0 | 1 | 0
[9 empty] | TOTAL EIL ITEMS | 139 |  | 111 |  | 28
|  |  | Total EIL items (Y&N) = |  | 139
LPD | [8 empty] | LPD
|  | Total |  | Closed |  | Remaining |  |  | Discipline | Total |  | Closed |  | Remaining
| Discipline | YES | NO | YES | NO | YES | NO |  |  | Y | N | YES | NO | YES | NO
| General Comment | 14 | 0 | 14 |  | 0 | 0 |  | General Comment | 14 | 0 | 14 | 0 | 0 | 0
[6 empty] | 0 | 0 |  | TOTAL | 14 | 0 | 14 | 0 | 0 | 0
| Total | 14 | 0 | 14 | 0 | 0 | 0 |  | TOTAL EIL ITEMS | 14 |  | 14 |  | 0
|  | Total EIL items (Y&N) = |  |  | 14 |  |  | PID | PID
PID | [8 empty] | Discipline | Total |  | Closed |  | Remaining |  | Discipline | Total |  | Closed
|  | Total |  | Closed |  | Remaining |  |  |  | Y | N | YES | NO | YES | NO |  | Y | N | YES | NO
| Discipline | YES | NO | YES | NO | YES | NO |  | Civil | 70 | 184 | 70 | 31 | 0 | 153 | Q | 70 | 184 | 70 | 31
| Civil | 70 | 184 | 70 | 31 | 0 | 153 |  | Electrical | 0 | 34 | 0 | 13 | 0 | 21 | P | 0 | 34 | 0 | 13
| Electrical |  | 34 |  |  | 0 | 34 |  | TOTAL | 70 | 218 | 70 | 44 | 0 | 174
| Total | 70 | 218 | 70 | 31 | 0 | 187 |  | TOTAL EIL ITEMS | 288 |  | 114 |  | 174
|  | Total EIL items (Y&N) = |  |  | 288 |  |  |  | OVER-ALL TOTAL "YES" ITEM = |  |  |  | 151
| OVER-ALL TOTAL "YES" ITEM = | [5 empty] | 151 |  | OVER-ALL TOTAL "NO" ITEM = |  |  |  | 290
| OVER-ALL TOTAL "NO" ITEM = | [5 empty] | 290
[9 empty] | OVER-ALL TOTAL "YES" ITEM CLOSED = |  |  |  | 151
| OVER-ALL TOTAL "YES" ITEM CLOSED = | [5 empty] | 151 |  | OVER-ALL TOTAL "NO" ITEM CLOSED = |  |  |  | 88
| OVER-ALL TOTAL "NO" ITEM CLOSED = | [5 empty] | 75
[9 empty] | OVER-ALL TOTAL "YES" ITEM REMAINING = |  |  |  | 0
| OVER-ALL TOTAL "YES" ITEM REMAINING = | [5 empty] | 0 |  | OVER-ALL TOTAL "NO" ITEM REMAINING = |  |  |  | 202
| OVER-ALL TOTAL "NO" ITEM REMAINING = | [5 empty] | 215

## KAUST
KAUST PERIMETER SECURITY SYSTEMS |  |  |  | Contract # |  | 6600029847 | PMCC No | 4B | Prepared By |  | Preparation date
EXCEPTION ITEM LIST |  |  |  | Date Prepared |  |  | REV | 0 | Approved By |  | Approval date
Contract Name: International Centre for Contracting
PMCC Area/ Facility: K12 Fence, NG Patrol Road, Island Wall, Khulays Culvert
Item NO | System NO.* | Discipline | Punch List Item | Y/N | Item Entry Date | ** Initiator | Initiator Org. | Status | Date Closed: | **Closed by: | Document ref: | admin only | Location |  | 2017-07-04
7 |  | Security | Not to relocate the exiting fence and its associated systems before installing and operating the IDAS components (MIDS and CCTV) FIRST on the new location. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 7 | Y | CLOSED | 42305
8 |  | Security | There shall be no physical gaps or system gaps on the relocated fence and new culvert and also it should not in any way affect the zone and/or the fence precedes and succeeds the relocated fence. Integration in the exiting fence and IDAS system shall exist without compromising integrity or functionality of the existing system and fence and related systems integration. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 8 | Y | CLOSED | 42305
9 |  | Security | The relocated shall be tested and commissioned by specialized Third Party security vendor and witnessed by security systems proponent. The test will also be made for the zone prior and after the relocated fence. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 9 | Y | CLOSED | 42305
10 |  | Security | Provide and install spikes on top of the new fence as approved by security Director | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 10 | Y | CLOSED | 42305
11 |  | Security | Provide and install thermal cameras (to be integrated with IDAS) at the end of the security wall fence on the island to cover any intrusion from the public beach to KAUST property through the shore and island. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 11 | Y | CLOSED | 42305
12 |  | Security | Professional cleaning shall be made for the security systems at the relocated part i.e. microwave sensors, cameras and inside field equipment enclosures and also cleaning for the IDAS zone from debris, jersey barriers, building materials, grass, weeds, plants, bags, garbage or any obstacle along the relocated part and the IDAS zone shall be sterilized from the aforementioned or any obstruction that will cause the system generate nuisance/false alarms. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 12 | Y | CLOSED | 42305
13 |  | Security | The configuration for the relocated fence shall be made to the existing system at SOC i.e. update the graphical user interface and electronic map with alarm management system. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 13 | Y | CLOSED | 42305
14 |  | Security | Update on the graphical interface and alarm system is required on the existing IDAS and alarm management system to reflect the new relocated fence/system and integration with existing IDAS. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (Covered in different PMCC) |  | 14 | Y | CLOSED | 42305
15 |  | Security | Coordination with security operation(s) shall be made during the fence relocation works. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2015-10-28 |  |  |  | New Wall Fence (not an item) |  | 15 | Y | CLOSED | 42305
16 |  | Security | Provide and install thermal cameras under the KHULAIS culvert and integrate it with the NEW IDAS | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | 2016-06-27 |  |  |  | Khulais Culvert |  | 16 | Y | CLOSED | 42548
17 |  | Security | Provide physical protection to prevent any intrusion from underneath the fence and culvert | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | To be deleted |  |  |  | Khulais Culvert | To be deleted | 17 | Y | OPEN
18 |  | Security | clean and clear all IDAS zones from debris, weeds, and construction materials. | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | To be deleted |  |  |  | New Wall Fence | To be deleted | 18 | Y | OPEN
19 |  | Security | No buildings or construction or trees should be near to the new wall fence (from outside) for at least 15 meters off! | Y | 2015-10-18 | Shadi Abdallah | Security | CLOSED | To be deleted |  |  |  | New Wall Fence | To be deleted | 19 | Y | OPEN
57 |  | Electrical | Perform Grounding Test of All Individual Grounding Rod (All Test will be witness by CxTeam Electrical) | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 57 | N | OPEN
58 |  | Electrical | Perform Insulation Test of All Electrical Cable for Lighting Post (All Test will be witness by CxTeam Electrical) | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 58 | N | OPEN
59 |  | Electrical | Perform Continuity Test of All Electrical Cable for Lighting Post (All Test will be witness by CxTeam Electrical) | Y | 2015-10-14 | Rommel& Ame | Cx-PMO | CLOSED | 2015-10-28 |  |  |  | Station 4 + 150 to 14 + 460 (combined with item 58) |  | 59 | Y | CLOSED | 42305
60 |  | Electrical | Provide Duct Sealant on All Electrical Conduit Entry in Lighting Post | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 60 | N | OPEN
61 |  | Electrical | All Direct Buried Electrical Cable Should be 600mm Depth from the Ground Level | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 61 | N | OPEN
62 |  | Electrical | Follow Back Filling Procedure as per NEC and Aramco Standard for Direct Burried Electrical Cables of Lighting Post | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 62 | N | OPEN
63 |  | Electrical | Provide Non-Metallic Weather Proof Identification Tag on All Ends of Electrical Cable of Lighting Post | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 63 | N | OPEN
64 |  | Electrical | Provide & Rivet a Stainless Steel Weather Proof Engrave Identification Plate on All Lighting Poles | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 64 | N | OPEN
65 |  | Electrical | Install All Remaining Lighting Post According to KAUST IFC Plan | Y | 2015-10-14 | Rommel& Ame | Cx-PMO | CLOSED | 2016-03-07 |  |  |  | Station 4 + 150 to 14 + 460 |  | 65 | Y | CLOSED | 42436
66 |  | Electrical | All Relocated RMU and Electrical Cables Should be Tested According to Safety Standard | Y | 2015-10-14 | Rommel& Ame | Cx-PMO | CLOSED | 2016-03-07 |  |  |  | Station 4 + 150 to 14 + 460 |  | 66 | Y | CLOSED | 42436
67 |  | Electrical | Provide RFI & Readable Approved Drawing for Cable Installation, Cable Layout & Cable Routing from SONAR 4 Going to Shelter 2 & Approve Material Submittals Prior to Commissioning | N | 2015-10-14 | Rommel& Ame | Cx-PMO | CLOSED | 2016-03-07 |  |  |  | Station 4 + 150 to 14 + 460 |  | 67 | N | CLOSED | 42436
68 |  | Electrical | Provide All Pre-Commissioning Test Form on All Individual Grounding Rod Prior to Commissioning of the Grounding Grid with CxTeam Electrical | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 68 | N | OPEN
69 |  | Electrical | Perform the Commissioning of the Grounding Grid with CxTeam Electrical | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 69 | N | OPEN
70 |  | Electrical | Provide All Pre-Commissioning Test Form on All Direct Buried Electrical Cable Prior to Commissioning of the Lighting Post | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 70 | N | OPEN
71 |  | Electrical | Perform the Commissioning of All Post Light with CxTeam Electrical | N | 2015-10-14 | Rommel& Ame | Cx-PMO | OPEN |  |  |  |  | Station 4 + 150 to 14 + 460 |  | 71 | N | OPEN
72 |  | Electrical | Provide Zinc Coated or Tin Coated Copper Terminal Lugs For Power Supply of All New Lighting Poles. | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2016-03-07 |  | SAES-P-104 Sec. 6 |  | Station 4 + 150 to 14 + 460 |  | 72 | Y | CLOSED | 42436
73 |  | Electrical | Provide Cable and Ferrule Tagging of Power Supply Cable of All New Lighting Poles on Both Ends of the Cable ( from - to ) and Reflect Its Circuit ID Number and Equipment Number Including All LP and DP Panels. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES-P-104 Sec. 6.10 |  | Station 4 + 150 to 14 + 460 |  | 73 | N | OPEN
74 |  | Electrical | Provide Pre-Commissioning Test Results of Power Cable for All New Lighting Poles with Request For Inspection form ( RFI ) Including Insulation Resistance Test and Continuity Test, Individual Lighting Poles. | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2016-03-07 |  | SAES-P-104 Sec. 13 |  | Station 4 + 150 to 14 + 460 |  | 74 | Y | CLOSED | 42436
75 |  | Electrical | Provide Request For Inspection form ( RFI ) and Approved Drawing for Cable Installation, Cable Layout and Cable Routing for All New Lighting Pole, from All LP Panels DP Panels and Going to All New Lighting Poles. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES-P-100 |  | Station 4 + 150 to 14 + 460 |  | 75 | N | OPEN
76 |  | Electrical | Provide Individual Equipment Grounding to All New Lighting Poles, All New LP and DP Panels Link to Main Grounding Grid and Grounding Rod ( Cad welded ) with 8 ft Minimum UL listed . | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2016-03-07 |  | SAES-P-111 Sec. 9 |  | Station 4 + 150 to 14 + 460 |  | 76 | Y | CLOSED | 42436
77 |  | Electrical | Provide Pre-Commissioning Results of Grounding Main Grid and Grounding Rod with 8 feet minimum UL Listed for All New Lighting Poles and All LP and DP Panels with Request For Inspection form ( RFI ). | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2016-03-07 |  | SAES-P-111 Sec. 13 |  | Station 4 + 150 to 14 + 460 |  | 77 | Y | CLOSED | 42436
78 |  | Electrical | Properly Dress Power Cable Supply Inside All LP and DP Panels and All New Lighting Poles with a Workmanship Like Manner. | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2016-03-07 |  | SAES-P-104 |  | Station 4 + 150 to 14 + 460 |  | 78 | Y | CLOSED | 42436
79 |  | Electrical | Provide Grounding Bushing on Conduit Pipe and Bonding Jumper Link to Main Grounding Grid for All New Lighting Poles. | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2015-10-28 |  | SAES-P-111 Sec. 9 |  | Station 4 + 150 to 14 + 460 (item deleted) |  | 79 | Y | CLOSED | 42305
80 |  | Electrical | Provide Duct Sealant on Unused Opening Entry, Gaps of Main Feeder of All New Lighting Pole, LP and DP Panels. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES-P-104 Sec. 15 |  | Station 4 + 150 to 14 + 460 |  | 80 | N | OPEN
81 |  | Electrical | Provide Pheonolic Tagging Attached on All New Lighting Poles, LP and DP Panels. Reflect Its Equipment ID and Equipment Number and Pole Number, Individual Lighting Pole. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES-P-104 |  | Station 4 + 150 to 14 + 460 |  | 81 | N | OPEN
82 |  | Electrical | Provide Post Marker for Proper Direction, Location, Routing & Distances of the Marker, Splicing Point Must Properly Identified and Fixing Screw for the Sign Must Be Stainless Steel, of Cable Routing Underground Duct Bank. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | KUAST SPECS 16170/ 3.02 |  | Station 4 + 150 to 14 + 460 |  | 82 | N | OPEN
83 |  | Electrical | Provide Individual Photocell Switches on All New Lighting Poles Twist-Lock Type and Shall Incorporate an Inherent Time Delay to Prevent Spurious Operations and Suitable for Continuous Operation in an Ambient Temperature Above 40°C. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 Sec 4.1.11 / Sec 4.1.12 |  | Station 4 + 150 to 14 + 460 |  | 83 | N | OPEN
84 |  | Electrical | Provide Request For Inspection form ( RFI ) and Approved Drawing and Specification for Lighting Pole Installation, Individual Lighting Pole. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 Sec 4.1 |  | Station 4 + 150 to 14 + 460 |  | 84 | N | OPEN
85 |  | Electrical | Provide Request for Instpection ( RFI ) of Approved Lighting Fixtures and Its Specification (UL listed). | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 Sec 4.2 |  | Station 4 + 150 to 14 + 460 |  | 85 | N | OPEN
86 |  | Electrical | Conduct Functional Test Individually to All New Lighting Fixtures and All Photocell Switches for the Integrity of the Equipment. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 |  | Station 4 + 150 to 14 + 460 |  | 86 | N | OPEN
87 |  | Electrical | Incomplete Installation of Individual Lighting Poles and Lighting Fixtures. (with photocel) | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 |  | Station 4 + 150 to 14 + 460 |  | 87 | N | OPEN
88 |  | Electrical | Incomplete Installation of Individual Grounding Rod and Link to Main Grid Grounding. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-111 |  | Station 4 + 150 to 14 + 460 |  | 88 | N | OPEN
89 |  | Electrical | Incomplete Installation of Individual Photocell Switches. | Y | 2015-10-13 | Ame / Rommel | Cx-PMO | CLOSED | 2015-10-28 |  | SAES-P-111 Sec. 9 |  | Station 4 + 150 to 14 + 460 (item deleted) |  | 89 | Y | CLOSED | 42305
90 |  | Electrical | Incomplete Detailed Drawing of Lighting Pole Installation. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-100 |  | Station 4 + 150 to 14 + 460 |  | 90 | N | OPEN
91 |  | Electrical | Incomplete Detailed Drawing of MV/LV Cable Installation | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-100 |  | Station 4 + 150 to 14 + 460 |  | 91 | N | OPEN
92 |  | Electrical | Conduct Illumination Test on All Lighting Fixtures as per Standard Require. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 Sec 5 |  | Station 4 + 150 to 14 + 460 |  | 92 | N | OPEN
93 |  | Electrical | Provide Request for Inspection (RFI) for MV/LV Cable Specification as per Project Materials Approval. | N | 2015-10-13 | Ame / Rommel | Cx-PMO | OPEN |  |  | SAES P-123 Sec 5 |  | Station 4 + 150 to 14 + 460 |  | 93 | N | OPEN
118 |  | Documentation | Provide All Engineering Documentation, Final Drawing Plans and Commissioning Folder in All Deciplines (Hard Copy and Soft Copy in AutoCAD & PDF File) that are Related to KPSS PMCC-04 Project, Prior to Handover (Closing of this Particular EIL will be Done after 30 days Submmission of All Documents) | N | 2015-10-14 | Rick | Cx-PMO | OPEN | [6 empty] | 118 | N | OPEN
119 |  | Civil | STA 4 + 150 towards Construction Access Gate: Concrete Capping's on fence columns are found missing at few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Crash Rated Wall (TYPE 12) STA 4+150 to Construction access Gate |  | 119 | Y | CLOSED | 42520
120 |  | Civil | Installation of G.I anti climb spikes not yet started for the new Fence | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Crash Rated Wall (TYPE 12) STA 4+150 to Construction Access Gate |  | 120 | Y | CLOSED | 42851
121 |  | Civil | Near Construction Access Gate: Area needs to be filled to match the design level/elevation. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-07-21 |  |  |  | In front of Construction Access Gate |  | 121 | N | CLOSED | 42572
122 |  | Civil | Incomplete work of all the elements of Fence (Fence Foundation, Installation of Precast Panels, Columns & Caps, Cable Trench, Lighting Poles and NG Patrol Road) | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | In front of Construction Access Gate |  | 122 | Y | CLOSED | 42851
123 |  | Civil | Construction Access Gate to KAUST Gate 1: Installation of G.I anti climb spikes not yet started for the new Fence | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-07-21 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 123 | Y | CLOSED | 42572
124 |  | Civil | Concrete Capping's are found missing at few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 124 | Y | CLOSED | 42520
125 |  | Electrical | Needs to attend remaining works of LV cable Trench for Lighting Poles, Cable Termination to Lighting Poles and Energization. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 125 | Y | CLOSED | 42883
126 |  | Electrical | NG Patrol road Lighting Poles: Filling and Grouting of Lighting pole base not yet done. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 126 | N | CLOSED | 42883
127 |  | Civil | Along North side of the Patrol Roads needs Grading, Backfilling and Clearing. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 127 | N | CLOSED | 42851
128 |  | Civil | All the construction debris (Asphalt Waist..etc.) found in between NG Patrol Road and New Fence shall be removed | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 128 | N | CLOSED | 42851
129 |  | Civil | Area between the Patrol road and Fence needs grading, levelling and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 129 | N | CLOSED | 42851
130 |  | Civil | All the temporary safety barriers and concrete blocks shall be removed and taken away. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Construction Access Gate to KAUST Gate 1 |  | 130 | N | CLOSED | 42851
131 |  | Civil | Under KAUST Bridge: Area underneath the bridge needs General Grading, Clearing and Compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Under KAUST Bridge |  | 131 | N | CLOSED | 42851
132 |  | Civil | Incomplete installation of fence panels observed in two corner locations | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Under KAUST Bridge |  | 132 | Y | CLOSED | 42520
133 |  | Civil | The Concrete fence panels at two locations were found made up of multiple horizontal concrete Panels. Please provide the Designers confirmation for this installation. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Under KAUST Bridge |  | 133 | N | CLOSED | 42851
134 |  | Civil | NG Patrol road edge of asphalt road not aligned properly, Needs cutting and clean. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Under KAUST Bridge |  | 134 | N | CLOSED | 42851
135 |  | Civil | KAUST Main Gate 1 towards Gate 2: Area east of Patrol road needs grading, filling and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 135 | N | CLOSED | 42851
136 |  | Electrical | NG Patrol road Lighting Poles: Filling and Grouting of Lighting pole base not yet done. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 136 | N | CLOSED | 42883
137 |  | Electrical | South side of the Bridge: needs to attend remaining works of LV cable Trench for Lighting Poles, Cable Termination to Lighting Poles and Energization. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 137 | Y | CLOSED | 42883
138 |  | Civil | NG Patrol road edge of asphalt road not aligned properly, Needs cutting and clean. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 138 | N | CLOSED | 42883
139 |  | Civil | All the temporary safety barriers and concrete blocks shall be removed and taken away. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 139 | N | CLOSED | 42851
140 |  | Civil | Needs to complete the asphalting wherever required along the NG Patrol. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 140 | Y | CLOSED | 42520
141 |  | Civil | Concrete Capping's on Fence columns are found missing at few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 141 | Y | CLOSED | 42851
142 |  | Civil | Installation of G.I anti climb spikes not yet started for the new Fence | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-07-21 |  |  |  | KAUST Main Gate 1 towards Gate 2 |  | 142 | Y | CLOSED | 42572
143 |  | Civil | KAUST Gate 2 area: Incomplete work of all the elements of fence (Fence Foundation, Installation of Precast Panels, Columns & Concrete Caps, Cable Trench, Lighting Poles and NG Patrol Road approaching to GATE 2) | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Gate 2 |  | 143 | Y | CLOSED | 42851
144 |  | Civil | Incomplete installation of Fence panels observed in few locations | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2015-10-28 |  |  |  | KAUST Gate 2 (item deleted) |  | 144 | Y | CLOSED | 42305
145 |  | Civil | Area near Gate 2 needs filling to match MOT Road Elevation | N | 2015-10-18 | PJ/KKA | Cx-PMO | CLOSED | 2017-04-26 |  |  |  | KAUST Gate 2 |  | 145 | N | CLOSED | 42851
146 |  | Civil | Reinstate the damages/broken edges of MOT Asphalt road due to construction activities. | N | 2015-10-18 | PJ/KKA | Cx-PMO | CLOSED | 2017-04-26 |  |  |  | KAUST Gate 2 |  | 146 | N | CLOSED | 42851
147 |  | Civil | South Side of Gate 2: Six panels are found missing or not installed | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | South side of Gate 2 |  | 147 | Y | CLOSED | 42520
148 |  | Civil | NG Patrol asphalt road not yet constructed. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | South side of Gate 2 |  | 148 | Y | CLOSED | 42851
149 |  | Electrical | The cable trench work, cable laying, Installation of Lighting poles and foundation not yet started. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | South side of Gate 2 |  | 149 | Y | CLOSED | 42883
150 |  | Civil | Area between the Fence and NG Patrol road needs grading, levelling and compacting. | N | 2015-10-18 | PJ/KKA | Cx-PMO | CLOSED | 2017-04-26 |  |  |  | South side of Gate 2 |  | 150 | N | CLOSED | 42851
151 |  | Civil | Area Between Gate 2 and Gate 3: Area between the fence and Patrol road needs grading, levelling and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Area Between Gate 2 and Gate 3 |  | 151 | N | CLOSED | 42851
152 |  | Electrical | Needs to complete remaining works of LV cable Trench for Lighting Poles, Cable Termination to Lighting Poles and Energization. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Area Between Gate 2 and Gate 3 |  | 152 | Y | CLOSED | 42883
153 |  | Civil | NG Patrol road edge of asphalt road not aligned properly, Needs cutting and clean. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Area Between Gate 2 and Gate 3 |  | 153 | N | CLOSED | 42851
154 |  | Electrical | NG Patrol road Lighting Poles: Filling and Grouting of Lighting pole base not yet done. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Area Between Gate 2 and Gate 3 |  | 154 | N | CLOSED | 42883
155 |  | Civil | Area between east of NG Patrol road and MOT road needs filling, grading and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Area Between Gate 2 and Gate 3 |  | 155 | N | CLOSED | 42851
156 |  | Civil | Area between new Fence and NG Patrol road needs proper fillings. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Area Between Gate 2 and Gate 3 |  | 156 | N | CLOSED | 42883
157 |  | Civil | KAUST Gate 3: Incomplete work of all the elements of fence (Fence Foundation, Installation of Precast Panels, Columns & Concrete Caps, Cable Trench, Lighting Poles and NG Patrol Road approaching to GATE 2) | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Gate 3 |  | 157 | N | CLOSED | 42851
158 |  | MEP | Installation of all MEP Manholes not yet started as shown in the IFC. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2015-10-28 |  |  |  | KAUST Gate 3 (item deleted) |  | 158 | Y | CLOSED | 42305
159 |  | Civil | Gate 3 area needs to be filled to match the required level | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Gate 3 |  | 159 | N | CLOSED | 42851
160 |  | Civil | South of Gate 3: Concrete Capping's on fence columns are found missing in few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | South of GATE 3 |  | 160 | Y | CLOSED | 42520
161 |  | Civil | Incomplete installation fence panels in all the corners. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | South of GATE 3 |  | 161 | Y | CLOSED | 42520
162 |  | Civil | NG Patrol road paving not started yet at south side of the Gate#3 | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | South of GATE 3 |  | 162 | Y | CLOSED | 42851
163 |  | Electrical | Needs to attend remaining works of LV Cable Trench for Lighting Poles, Cable Termination to Lighting Poles and Energization. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | South of GATE 3 |  | 163 | Y | CLOSED | 42883
164 |  | Civil | China Gate: Incomplete work of all the elements of fence (Fence Foundation, Installation of Precast Panels, Columns & Concrete Caps, Cable Trench, Lighting Poles and NG Patrol Road) | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | South of GATE 3 |  | 164 | Y | CLOSED | 42851
165 |  | Civil | Area needs to be filled to match the required level | N | 2015-10-18 | PJ/KKA | Cx-PMO | CLOSED | 2017-05-28 |  |  |  | South of GATE 3 |  | 165 | N | CLOSED | 42883
166 |  | Civil | Area between fence and NG Patrol road towards east up to MOT road needs grading, filling and compacting | N | 2015-10-18 | PJ/KKA | Cx-PMO | CLOSED | 2017-05-28 |  |  |  | South of GATE 3 |  | 166 | N | CLOSED | 42883
167 |  | Civil | South of China GATE: Concrete Capping's on fence columns are found missing in few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | South of China GATE |  | 167 | Y | CLOSED | 42520
168 |  | Civil | Wadi Wesami Culvert No.3: Area between the concrete parapet and Patrol road need Filling, grading and Compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Culvert No.3: |  | 168 | N | CLOSED | 42883
169 |  | Civil | The backfilling and compaction at the Lighting Poles bases is found incomplete. Need to complete proper backfilling and compaction at all applicable locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Culvert No.3: |  | 169 | Y | CLOSED | 42851
170 |  | Civil | Need to verify the elevation level of the new fence with respect to NG patrol road. Foundation of fence exposed above NG asphalt road which is not acceptable. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Culvert No.3: |  | 170 | Y | CLOSED | 42851
171 |  | Civil | Wadi Wesami Culvert No.4: Area between the concrete parapet and Patrol road need Filling, grading and Compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Culvert No.4 |  | 171 | N | CLOSED | 42851
172 |  | Civil | The backfilling and compaction at the Lighting Poles bases is found incomplete. Need to complete proper backfilling and compaction at all applicable locations. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Culvert No.4 |  | 172 | N | CLOSED | 42851
173 |  | Civil | Need to verify the elevation level of the new fence with respect to NG patrol road. Foundation of fence exposed above NG asphalt road which is not acceptable. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Culvert No.4 |  | 173 | Y | CLOSED | 42851
174 |  | Civil | MOI Area: Area adjacent to MOI land needs filling, grading and compaction on both sides of NG Patrol Road | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | MOI land area |  | 174 | N | CLOSED | 42851
175 |  | Civil | NG Patrol Road asphalt work is incomplete | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | MOI land area |  | 175 | Y | CLOSED | 42851
176 |  | Electrical | Street Lighting Poles found missing or not installed along NG patrol road near MOI Land | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 176 | Y | CLOSED | 42883
177 |  | Civil | The backfilling and compaction at the Lighting Poles bases is found incomplete. Need to complete proper backfilling and compaction at all applicable locations. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 177 | N | CLOSED | 42883
178 |  | Civil | Construction Debris shall be removed from the area between Fence and MOI land. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 178 | N | CLOSED | 42883
179 |  | Civil | At the north west corner of the MOI Land area between fence and patrol road needs filling, grading and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 179 | N | CLOSED | 42883
180 |  | Civil | Patrol road merging with the existing old road needs marking as a safety precaution. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 180 | N | CLOSED | 42883
181 |  | Civil | Area between new MOT road and NG Patrol road along South Fence needs filling, grading and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 181 | N | CLOSED | 42883
182 |  | Civil | Old NG shade structure shall be dismantled with coordination of KAUST Security. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | MOI land area |  | 182 | N | CLOSED | 42883
183 |  | Civil | Concrete capping's on fence columns are found missing in few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | MOI land area |  | 183 | Y | CLOSED | 42520
184 |  | Civil | KAUST Gate 4: Fence panel Merging, LV Cable trenching, Cable Laying, Street Lighting Poles & foundation incomplete | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | KAUST Gate 4 |  | 184 | Y | CLOSED | 42851
185 |  | Civil | KAUST Gate 4 area needs filling to match the design level/elevation. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | KAUST Gate 4 |  | 185 | N | CLOSED | 42883
186 |  | Civil | All the temporary safety barriers and concrete blocks towards Gate 4 shall be removed and taken away | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | KAUST Gate 4 |  | 186 | N | CLOSED | 42883
187 |  | Civil | Gate 4 South Area: The area between fence and Patrol road needs filling, grading and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Gate 4 South Area |  | 187 | N | CLOSED | 42883
188 |  | Civil | The backfilling and compaction at the Lighting Poles bases is found incomplete. Need to complete proper backfilling and compaction at all applicable locations. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Gate 4 South Area |  | 188 | N | CLOSED | 42883
189 |  | Electrical | Needs to complete remaining works of LV Cable Trench for Lighting Poles, Cable Termination to Lighting Poles and Energization. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Gate 4 South Area |  | 189 | Y | CLOSED | 42883
190 |  | Civil | Concrete Capping's on Fence columns are found missing in few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Gate 4 South Area |  | 190 | Y | CLOSED | 42520
191 |  | Civil | Private Encroachment: NG Patrol road is discontinued due the private Encroachment needs to be completed. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | Private Encroachment |  | 191 | Y | CLOSED | 42851
192 |  | Electrical | Area of Private encroachment and further south: LV Cable Trench & Cables laying, Lighting poles/foundation found incomplete | N | 2015-10-18 | PJ/KKA | M&U-TS | OPEN |  |  |  |  | Private Encroachment (Combined with item 191 |  | 192 | N | OPEN
193 |  | Civil | Towards south of the existing encroachment: The Area between Fence and NG Patrol needs filling, grading and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 | [5 empty] | 193 | N | CLOSED | 42883
194 |  | Civil | The area between MOT road and NG Patrol road needs filling, grading and compacting. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 | [5 empty] | 194 | N | CLOSED | 42883
195 |  | Civil | Needs to evaluate the elevation difference between MOT Road and NG Patrol road. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 | [5 empty] | 195 | N | CLOSED | 42883
196 |  | Civil | Fence adjacent to Corniche road up to the Wadi Khulays Culvert: Entire Fence and its elements (Lighting Poles, LV cable trench, cables, Lighting poles, NG Patrol Road) are found missing. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 | [5 empty] | 196 | Y | CLOSED | 42851
197 |  | Civil | On Wadi Khulays Culvert: Installation of Fence, Concrete Capping's on Fence Columns are incomplete. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Wadi Khulays Culvert top |  | 197 | Y | CLOSED | 42520
198 |  | Civil | From Wadi Khulays Culvert towards Beach area: Installation of Fence Panels are incomplete. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | From Wadi Khulays Culvert towards beach area |  | 198 | Y | CLOSED | 42520
199 |  | Civil | Area between existing road and Fence needs to be properly filled. | N | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | From Wadi Khulays Culvert towards beach area |  | 199 | N | CLOSED | 42883
200 |  | Civil | Corner Fence Panels are missing; needs to be installed/completed. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | From Wadi Khulays Culvert towards beach area |  | 200 | Y | CLOSED | 42520
201 |  | Civil | Concrete Capping's on Fence columns are found missing in few locations. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | From Wadi Khulays Culvert towards beach area |  | 201 | Y | CLOSED | 42520
202 |  | Civil | NG Patrol needs rectification; to be completed. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-04-26 |  |  |  | From Wadi Khulays Culvert towards beach area |  | 202 | Y | CLOSED | 42851
203 |  | Civil | Fence panels are missing near Transformer area towards the beach (west fence panel) | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Beach area |  | 203 | Y | CLOSED | 42520
204 |  | Civil | Fence Panels and Capping found missing near the end of K12 | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Beach area |  | 204 | Y | CLOSED | 42520
205 |  | Electrical | Evaluate Lighting poles requirement at the fence west edge. | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2017-05-28 |  |  |  | Beach area |  | 205 | Y | CLOSED | 42883
206 |  | Civil | Installation of K8 Fence Panels and Capping's are incomplete | Y | 2015-10-18 | PJ/KKA | M&U-TS | CLOSED | 2016-05-30 |  |  |  | Beach area |  | 206 | Y | CLOSED | 42520
END

## LPD
EXCEPTION ITEM LIST
Saudi Aramco 6133 (02/99)
BI No.: |  |  | Facilty |  | System No. |  |  |  |  | Date:
PMCC-04BKAUST Perimeter Security Systems | [9 empty] | 2015-09-09
Item | Item Description | Item Entry Date | Schedule Date for Completion | Required for Start-Up | Covered by Project | Requested By | Status | Date Closed: | **Closed by: | Remarks
1 | Complete installation and of all precast panels, columns and columns caps. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
2 | Complete vertical alignment of precast panels, columns and lighting poles. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
3 | Complete asphalting the Patrol Road. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
4 | Complete the backfilling and compaction for all asphalt patrol road shoulder | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
5 | Complete the backfilling and compaction around Shelter #2. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2016-06-16 | Ehsan Abu-Saif | PMCC 04A-SONAR
6 | Wall and floor openings at Shelter #2 to be completely sealed with approved sealant material. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2016-06-16 | Ehsan Abu-Saif | PMCC 04A-SONAR
7 | Complete all cables/equibment tagging and identification at Shelter #2. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2016-06-16 | Ehsan Abu-Saif | PMCC 04A-SONAR
8 | Remove all construction debries and stored material from Shelter #2 and improve the housekeeping. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2016-06-16 | Ehsan Abu-Saif | PMCC 04A-SONAR
9 | Complete installation of anti climb spikes on the crash rated wall. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
10 | Complete all cable dressing, cable termination and grouding of the lighting poles. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
11 | Remove all construction debries and sand from the patrol road and improve the housekeeping generally. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
12 | Complete the backfilling and compaction around lighting poles. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
13 | Complete the final alignment and bolt tightening of all electrical lighting post and fixtures | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
14 | Complete all lighting poles, cables and panels' identification and tagging. | 2015-10-13 |  | Yes |  | SA/LPD | CLOSED | 2017-05-28 |  | Closed in KAUST comment
2016-05-17
2016-05-17
2016-05-17
2016-05-17
2016-05-17
2016-05-17
2016-05-17
1
2
3
4
5
6
7
8
9
0
R35
UTILITY
REVISION
UTH. GAS PLANTS

## PID
KAUST PERIMETER SECURITY SYSTEMS | [9 empty] | Distribution Date:
Distributed by:
Site (Project) :
This list is for the project indicated by the "x" in the box to the right.
Contract Name: International Centre for Contracting (ICC) | [5 empty] | Contract Number: |  | PMCC No. 04B |  |  | Contract MCC Date:
PMCC Area: Crash Rated Wall (Type K12) Sta.4+150 to Sta.14+530), Island Precast Wall (Sta.4+530 to 14+834), Patrol road & 10m Pole Lighting (Sta.4+150 to 14+460), Wadi Khulais Culvert | [5 empty] | 6600029847
Item NO | System NO.* | Punch List Item | Y/N | Item Entry Date | ** Initiator | Initiator Org. | Status | Date Closed: | **Closed by: | Document ref: | admin only | Location |  | 2017-07-04
1 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-04-29 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 1 | Y | CLOSED | 42854
2 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-04-29 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 2 | Y | CLOSED | 42854
3 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 3 | N | OPEN
4 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-04-29 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 4 | Y | CLOSED | 42854
5 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12). | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2016-07-21 |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 5 | Y | CLOSED | 42572
6 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-04-29 |  | SAES-H-003 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 6 | N | CLOSED | 42854
7 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-05-07 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 7 | Y | CLOSED | 42862
8 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 8 | Y | CLOSED | 42870
9 | Q | All damaged asphalt pavement in new patrol road shall be repaired as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 9 | N | OPEN
10 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 10 | N | OPEN
11 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 11 | N | OPEN
12 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 12 | N | OPEN
13 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 13 | N | OPEN
14 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-11 | JAD/JBR | PID | CLOSED | 2015-12-15 |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 14 | N | CLOSED | 42353
15 | Q | Provide and apply non-shrink grout below base plate of lighting pole foundations at New patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 15 | N | OPEN
16 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 16 | N | OPEN
17 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 1900-01-07 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 17 | N | OPEN
18 | Q | All damaged PC elements ( wall panel,column , caps) shall be repaired using approved repair materials. | N | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-04-29 |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 18 | N | CLOSED | 42854
19 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 19 | N | OPEN
20 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-04-29 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 4+150- Sta 5+000 |  | 20 | Y | CLOSED | 42854
21 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2016-04-06 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 21 | Y | CLOSED | 42466
22 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-11 | JAD/JBR | PID | CLOSED | 2016-04-06 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 22 | N | CLOSED | 42466
23 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 23 | Y | CLOSED | 42865
24 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12). | Y | 2015-10-11 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 24 | Y | CLOSED
25 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-11 | JAD/JBR | PID | CLOSED | 2016-04-06 |  | SAES-H-003 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 25 | N | CLOSED | 42466
26 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 26 | Y | CLOSED | 42865
27 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | Y | 2015-10-11 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 27 | Y | CLOSED | 42870
28 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 28 | N | OPEN
29 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 29 | N | OPEN
30 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 30 | N | OPEN
31 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 31 | N | OPEN
32 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 32 | N | OPEN
33 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-11 | JAD/JBR | PID | CLOSED | 2015-12-15 |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 33 | N | CLOSED | 42353
34 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 34 | N | OPEN
35 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-11 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 35 | N | OPEN
36 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 36 | N | OPEN
37 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 37 | N | OPEN
38 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 5+000- Sta 6+000 |  | 38 | N | OPEN
39 | Q | Complete the rectification of LBE # 523 with regards to one time backfilling and asphalt paving activity of ductbank road crossing at Sta. 6+200. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-06-13 |  | LBE # 523, SAES-A-114, SAES-Q-006 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 39 | Y | CLOSED | 42534
40 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-06-02 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 40 | Y | CLOSED | 42523
41 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-04-11 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 41 | Y | CLOSED | 42471
42 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-04-11 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 42 | N | CLOSED | 42471
43 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 43 | Y | CLOSED | 42865
44 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-12 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 44 | Y | CLOSED
45 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-04-11 |  | SAES-H-003 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 45 | N | CLOSED | 42471
46 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 46 | Y | CLOSED | 42865
47 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 47 | Y | CLOSED | 42870
48 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 48 | N | OPEN
49 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 49 | N | OPEN
50 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 50 | N | OPEN
51 | Q | Complete the rectification of LBE # 508 with regards to the Non-conformance test results for Hot Asphalt Materials (Sta. 6+200-6+300, 6+350-6+455, 6+400-6+600- Wearing course. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | LBE # 508, SAES-Q-006 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 51 | Y | CLOSED | 42870
52 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 52 | N | OPEN
53 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 53 | N | OPEN
54 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-12 | JAD/JBR | PID | CLOSED | 2015-12-15 |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 54 | N | CLOSED | 42353
55 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 55 | N | OPEN
56 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 56 | N | OPEN
57 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 57 | N | OPEN
58 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 58 | N | OPEN
59 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 6+000- Sta 7+000 |  | 59 | N | OPEN
60 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 60 | Y | CLOSED | 42507
61 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 61 | Y | CLOSED | 42507
62 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 62 | N | OPEN
63 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 7+000- Sta 8+000 | 1 | 63 | N | OPEN
64 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12). | Y | 2015-10-12 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 64 | Y | CLOSED
65 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | SAES-H-003 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 65 | N | OPEN
66 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2017-05-06 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 66 | Y | CLOSED | 42861
67 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | Y | 2015-10-12 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 67 | Y | CLOSED | 42870
68 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 68 | N | OPEN
69 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 69 | N | OPEN
70 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-12 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 70 | N | OPEN
71 | Q | Rectification of LBE # 508 with regards to the non-conformance test report of Hot Asphalt Materials at Sta 7+200-7+250- Wearing Course, Sta. 7+250-7+350- Binder course, Sta. 7+350-7+800- Wearing course. | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | LBE # 508, SAES-Q-006 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 71 | Y | CLOSED | 42870
72 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 72 | N | OPEN
73 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 73 | N | OPEN
74 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 74 | N | OPEN
75 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 75 | N | OPEN
76 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 76 | N | OPEN
77 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 77 | N | OPEN
78 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 78 | N | OPEN
79 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 7+000- Sta 8+000 |  | 79 | N | OPEN
80 | Q | Complete the rectification of LBE # 523 with regards to the one time backfilling and asphalt paving activity of road crossing electrical duct bank at Sta. 8+500. | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2016-06-13 |  | LBE # 523, SAES-A-114, SAES-Q-006 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 80 | Y | CLOSED | 42534
81 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 81 | Y | CLOSED | 42681
82 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 82 | Y | CLOSED | 42681
83 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 83 | N | OPEN
84 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 84 | Y | CLOSED | 42681
85 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-13 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 85 | Y | CLOSED
86 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-13 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | SAES-H-003 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 86 | N | CLOSED | 42681
87 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 87 | Y | CLOSED | 42865
88 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006 | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 88 | Y | CLOSED | 42870
89 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 89 | N | OPEN
90 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 90 | N | OPEN
91 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 91 | N | OPEN
92 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 92 | N | OPEN
93 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 93 | N | OPEN
94 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 94 | N | OPEN
95 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 95 | N | OPEN
96 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 96 | N | OPEN
97 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 97 | N | OPEN
98 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 98 | N | OPEN
99 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-13 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 8+000- Sta 9+000 |  | 99 | N | OPEN
100 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-13 | JAD/JBR | PID | CLOSED | 2017-05-06 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 100 | Y | CLOSED | 42861
101 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 101 | Y | CLOSED | 42859
102 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 102 | N | OPEN
103 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-06 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 103 | Y | CLOSED | 42861
104 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-14 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 104 | Y | CLOSED
105 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | SAES-H-003 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 105 | N | OPEN
106 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-06 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 106 | Y | CLOSED | 42861
107 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-13 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 9+000- Sta 10+000 | 1 | 107 | N | CLOSED | 42868
108 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 108 | N | OPEN
109 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 109 | N | OPEN
110 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 110 | N | OPEN
111 | Q | Complete the Rectification of LBE # 517 with regards to the non-application of tack coat on Binder course prior to the application of wearing course.Sta 9+650- 9+700. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | LBE # 517, SAES-Q-006 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 111 | N | OPEN
112 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 112 | N | OPEN
113 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 113 | N | OPEN
114 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-03-22 |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 114 | N | CLOSED | 42451
115 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 115 | N | OPEN
116 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 116 | N | OPEN
117 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 117 | N | OPEN
118 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 118 | N | OPEN
119 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 9+000- Sta 10+000 |  | 119 | N | OPEN
120 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 120 | Y | CLOSED | 42681
121 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 121 | Y | CLOSED | 42681
122 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 122 | N | OPEN
123 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 123 | Y | CLOSED | 42681
124 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12). | Y | 2015-10-14 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 124 | Y | CLOSED
125 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-11-07 |  | SAES-H-003 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 125 | N | CLOSED | 42681
126 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-06 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 126 | Y | CLOSED | 42861
127 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-06 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 127 | Y | CLOSED | 42861
128 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 128 | N | OPEN
129 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 129 | N | OPEN
130 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 130 | N | OPEN
131 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 131 | N | OPEN
132 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 132 | N | OPEN
133 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 133 | N | OPEN
134 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 134 | N | OPEN
135 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 135 | N | OPEN
136 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 136 | N | OPEN
137 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 137 | N | OPEN
138 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 10+000- Sta 11+000 |  | 138 | N | OPEN
139 | Q | Complete the rectification of LBE # 523 with regards to the one time backfilling and asphalt paving activity of road crossing electrical duct bank at Sta. 11+150. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-06-13 |  | LBE # 523, SAES-A-114, SAES-Q-006 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 139 | Y | CLOSED | 42534
140 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 140 | Y | CLOSED | 42507
141 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 141 | Y | CLOSED | 42507
142 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 142 | N | OPEN
143 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 143 | Y | CLOSED | 42865
144 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-14 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 144 | Y | CLOSED
145 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | SAES-H-003 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 145 | N | CLOSED | 42507
146 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 146 | Y | CLOSED | 42865
147 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006 | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 147 | Y | CLOSED | 42870
148 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 148 | N | OPEN
149 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 149 | N | OPEN
150 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 150 | N | OPEN
151 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 151 | N | OPEN
152 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 152 | N | OPEN
153 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 153 | N | OPEN
154 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 154 | N | OPEN
155 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 155 | N | OPEN
156 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 156 | N | OPEN
157 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 157 | N | OPEN
158 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 11+000- Sta 12+000 |  | 158 | N | OPEN
159 | Q | Complete the recttification of LBE # 507 with regards to the fill placement of unfiltered backfill materials along Security perimeter Fence Project | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | LBE # 507, SAES-A-114 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 159 | N | OPEN
160 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 160 | Y | CLOSED | 42507
161 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-05-17 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 161 | Y | CLOSED | 42507
162 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 162 | N | OPEN
163 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114, | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 163 | Y | CLOSED | 42865
164 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-14 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 164 | Y | CLOSED
165 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | SAES-H-003 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 165 | N | OPEN
166 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 12+000- Sta 13+000 | 1 | 166 | N | OPEN
167 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006 | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 12+000- Sta 13+000 | 1 | 167 | N | OPEN
168 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 168 | N | OPEN
169 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 169 | N | OPEN
170 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 170 | N | OPEN
171 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 171 | N | OPEN
172 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 172 | N | OPEN
173 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 173 | N | OPEN
174 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 174 | N | OPEN
175 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 175 | N | OPEN
176 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 176 | N | OPEN
177 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 177 | N | OPEN
178 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 12+000- Sta 13+000 |  | 178 | N | OPEN
179 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2016-06-02 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 179 | Y | CLOSED | 42523
180 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 180 | Y | CLOSED | 42859
181 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 181 | N | OPEN
182 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-05-10 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 182 | Y | CLOSED | 42865
183 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-14 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 183 | Y | CLOSED
184 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | SAES-H-003 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 184 | N | OPEN
185 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | N | 2015-10-14 | JAD/JBR | PID | CLOSED | 2017-06-14 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 13+000- Sta 14+000 | 1 | 185 | N | CLOSED | 42900
186 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006 | N | 2015-10-14 | JAD/JBR | PID | OPEN |  |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 13+000- Sta 14+000 | 1 | 186 | N | OPEN
187 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 187 | N | OPEN
188 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 188 | N | OPEN
189 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 189 | N | OPEN
190 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 190 | N | OPEN
191 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 191 | N | OPEN
192 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 192 | N | OPEN
193 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 193 | N | OPEN
194 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 194 | N | OPEN
195 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 195 | N | OPEN
196 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 196 | N | OPEN
197 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 13+000- Sta 14+000 |  | 197 | N | OPEN
198 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2016-06-09 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 198 | Y | CLOSED | 42530
199 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 199 | Y | CLOSED | 42859
200 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 14+000- Sta 14+840 | 1 | 200 | N | OPEN
201 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 201 | Y | CLOSED | 42859
202 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12), | Y | 2015-10-15 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 202 | Y | CLOSED
203 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | SAES-H-003 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 203 | N | OPEN
204 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 204 | Y | CLOSED | 42859
205 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006 | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of works, SAES-Q-006 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 205 | Y | CLOSED | 42859
206 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 206 | N | OPEN
207 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 207 | N | OPEN
208 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 208 | N | OPEN
209 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 209 | N | OPEN
210 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 210 | N | OPEN
211 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 211 | N | CLOSED | 42859
212 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 212 | N | CLOSED | 42859
213 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 213 | N | CLOSED | 42859
214 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-A-114 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 214 | N | CLOSED | 42859
215 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 215 | N | OPEN
216 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 216 | N | OPEN
217 | Q | Complete the sub grade preparation, layer by layer backfilling of select fill and compaction prior to the installation of precast foundation (K12). | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-15 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | New Patrol Road, Sta 14+000- Sta 14+840 |  | 217 | Y | CLOSED | 42870
218 | Q | Complete the installation, alignment of K12 precast foundation, columns, wall panels and column caps at Security Perimeter Fence Project. | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 218 | Y | CLOSED | 42859
219 | Q | Complete the removal, surface preparation and application of non shrink grout for all security perimeter fence PC wall panel lifting hooks and threaded inserts. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-Q-010, IFC drawing VA-Q-846521-001,002, 006,- 00 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 219 | N | OPEN
220 | Q | Complete the layer by layer backfilling of select/general fill and compaction below PC foundations and sides of PC columns and walls of Security Perimeter Fence Foundation as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, SAES-A-114, IFC Drawing VA-S-846505-002-0F1 |  | Brick wall area Sta 0+000- Sta 0+350 | 1 | 220 | N | OPEN
221 | Q | Provide and complete the installation of anti- climb fence spikes for Security Perimeter Fence (K12). | Y | 2015-10-15 | JAD/JBR | PID | CLOSED |  |  | Scope of Works, IFC drawing VA-S-846507- 001, 002, 005,007, 008 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 221 | Y | CLOSED
222 | Q | Complete the surface preparation and application of bitumious paints in all special/ non special precast column,wall panels, column caps and footings (K12) prior to backfilling activity. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | SAES-H-003 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 222 | N | CLOSED | 42863
223 | Q | Complete the layer by layer backfilling of base course in new patrol road prior to the asphalt paving activity as per SAES-Q-006. | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of Works, SAES-A-114, IFC Drawing VA-Q- |  | Brick wall area Sta 0+000- Sta 0+350 |  | 223 | Y | CLOSED | 42859
224 | Q | Complete all the asphalt paving activity for new patrol road as per SAES-Q-006. | Y | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-04 |  | Scope of works, SAES-Q-006 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 224 | Y | CLOSED | 42859
225 | Q | All damaged asphalt pavement in new patrol road road shall be repair as per requirement of Schedule Q and SAES-Q-006. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Schedule Q, Gen. Para. 1.2 SAES-Q-006 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 225 | N | CLOSED | 42863
226 | Q | Submit for review and acceptance of the Core Density Test report of the Binder Course paving for new patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | Brick wall area Sta 0+000- Sta 0+350 |  | 226 | N | CLOSED | 42863
227 | Q | Submit for review and acceptance of the Core Density Test report of the Wearing Course paving for new patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Scope of Works, SAES-Q-006, Sec. 5.5.4.6B & 5.5.3B |  | Brick wall area Sta 0+000- Sta 0+350 |  | 227 | N | CLOSED | 42863
228 | Q | Final inspection for binder course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | Brick wall area Sta 0+000- Sta 0+350 |  | 228 | N | CLOSED | 42863
229 | Q | Final inspection for wearing course Asphalt Paving shall be performed at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Scope of Works, SAES-Q-006, Sec.5.5.4.6A & 5.5.4.5A (SAIC-Q-1044) |  | Brick wall area Sta 0+000- Sta 0+350 |  | 229 | N | CLOSED | 42863
230 | Q | Complete the installation and alignment of lighting pole foundations with 10 m high pole at new patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | IFC drawing VA-S-846505-002-0F1 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 230 | N | CLOSED | 42863
231 | Q | Provide and apply non-shrink grout under base plate of lighting pole foundations at New patrol road. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Proj. Spec. K55-A-VE-846422-10 of 11 Statement G.SAES-Q-005, SAES-Q-010, IFC drawing VA-S-846505-002-0F1 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 231 | N | CLOSED | 42863
232 | Q | Complete the layer by layer backfilling of select fill and compaction of electrical trench as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Project Specs- 02210, Sect. 3.03, SAES-A-114 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 232 | N | CLOSED | 42863
233 | Q | Complete the layer by layer backfilling of select fill and compaction around electrical pole foundation as per SAES-A-114. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Scope of Works, SAES-A-114 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 233 | N | CLOSED | 42863
234 | Q | All damaged precast members shall repaired using approved repair materials. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Schedule Q, Gen. Para. 1.2 |  | Brick wall area Sta 0+000- Sta 0+350 |  | 234 | N | OPEN
235 | Q | Complete the layer by layer backfilling of select fill and compaction of new patrol road asphalt pavement shoulders & establish the required width and final grade elevation with 1:3 slope sides of electircal lighting pole and on side of New Security Perimeter Fence (K12). | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2017-05-08 |  | Scope of Works, SAES-A-114, IFC Drawing IC-SD-846553-101-00, VA-S-846505-003-0FI |  | Brick wall area Sta 0+000- Sta 0+350 |  | 235 | N | CLOSED | 42863
236 | Q | Subcontractor Aramco proceeded with the cleaning/removal of the sprayed MC-1 on the surfaces of the precast concrete panels and columns by sandblasting without submitting method of statement as previously adviced. It resulted to further damage of the PC Panels/Columns, Physical appearance, color and texture. The sandblasted areas appeared darker, texture diminished and sprayed bituminous coat on the lower portions are removed. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Reference LBE 504 dated 8-01-15 . Clear violation of Schedule Q-Gen. requirement, Clause 1.2 and Attachment IV, Clause 3.2. , PCI MNL-117 |  | Patrol Road ,Sta. KM. 9+200 to 9+600 (approx.) |  | 236 | N | OPEN
237 | Q | Complete grouting and repair works of the special PC wall panels connection. | N | 2015-10-15 | JAD/JBR | PID | CLOSED | 2016-03-22 |  | Scope of Works , SAES-Q-012, IFC Drawing # SK-FCC-846522 , SHT. 101/2&4 , rev 00 |  | Under existing Bridge |  | 237 | N | CLOSED | 42451
238 | Q | Complete repair works of Tie rod holes and concrete defects on the surfaces and construction joints on walls, parapet walls and slabs. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works , Approved MS Repair Procedure of Concrete Defects |  | Al Wadi Khulais Box Culvert |  | 238 | N | OPEN
239 | Q | Conduct slope test on the channel bed of the box culvert. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Scope of Works, IFC Drawing # VA-847047 |  | Al Wadi Khulais Box Culvert |  | 239 | N | OPEN
240 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.4+150- 5+000 |  | 240 | N | OPEN
241 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.5+000- 6+000 |  | 241 | N | OPEN
242 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.6+000- 7+000 |  | 242 | N | OPEN
243 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.7+000- 8+000 |  | 243 | N | OPEN
244 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.8+000- 9+000 |  | 244 | N | OPEN
245 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.9+000- 10+000 |  | 245 | N | OPEN
246 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.10+000- 11+000 |  | 246 | N | OPEN
247 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.12+000- 13+000 |  | 247 | N | OPEN
248 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.13+000- 14+000 |  | 248 | N | OPEN
249 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | All Area Sta.14+000- 14+840 |  | 249 | N | OPEN
250 | Q | Complete the cleaning of all area as per Scope of Works Item 1.04. | N | 2015-10-15 | JAD/JBR | PID | OPEN |  |  | Project Specs. Section 01700, Gen., Item 1.04 |  | Brick wall area, Sta 0+000- Sta 0+350 |  | 250 | N | OPEN
257 | P | Prior to grouting of concrete foundations, Check the horizontal and vertical alignment of all installed lighting pole assembly. Submit the visual inspection of concrete foundations from civil and approved survey reports by Saudi Aramco surveyor. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 257 | N | CLOSED | 42919
258 | P | Mounting of base plate on the foundation shall complete with nuts and plain round washers both top and bottom of the base plate | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 258 | N | CLOSED | 42919
259 | P | Hand hole cover are properly tight and close and replace or repair rubber gasket | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 259 | N | CLOSED | 42919
260 | P | Repair any damage coating as per manufacturer's recommendations. All Anchor bolts thread shall be exposed minimum to a minimum of 2-3 threads. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 260 | N | CLOSED | 42919
261 | P | Complete the installation of remaining road lightings with hot dipped galvanized lighting pole, HID lighting fixture, 3C x 4 mm2 CU/XLPE/PVC multi-core cable, terminal block and fuse box assembly, stainless steel bolts SS 304 and including all accessories as per IFC drawings and approved shop drawings. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123, SAES-P-104 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 | 1 | 261 | N | CLOSED | 42919
262 | P | Replace the galvanized bolts for all installed hot dipped galvanized lighting poles with stainless steel SS 304 materials suitable for severe corrosive area of all lighting pole arm assembly. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-100 Section 9, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 262 | N | OPEN
263 | P | Replace the existing installed LV cables (power cables) which are being cut near the lighting pole with new cables. Perform thermite welding of below grade connections of copper-jacketed grounding rods and grounding cables. Raise RFI for material receiving inspections of molds, powder and raise RFI for thermite weld connections. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | SAES-P-100, SAES-P-104, SAES-P-111, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 | 1 | 263 | N | CLOSED | 42919
264 | P | Perform termite cadwelding for all light poles to connect ground rod and grounding cable and Provide bituminous paint, rubber and PVC electrical tape after thermite welding.Raise RFI for sand bedding, cable installation, placement of sand covering, red tiles and yellow warning tapes. NOTE: splicing of power cable (power circuit) is not acceptable except for grounding cable. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | SAES-P-100, SAES-P-104, SAES-P-111, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 264 | N | CLOSED | 42919
265 | P | Perform continuity for power cable, equipment grounding conductors (EGC), Steel Wire Armour (SWA) of power cable and insulation resistance test of low voltage power cables for all road lightings. Ensure individual continuity test are being perform for all equipment grounding conductors (EGC) and Steel Wire Armour (SWA) of power cable. Use calibrated test instruments. Raise RFI for testing of cables. Records all the test results in the Saudi Aramco pre-commissioning forms. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-04 |  | Project Specifications Section 16120/16999, Scope of Work Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 | 1 | 265 | N | CLOSED | 42920
266 | P | For all road lightings, Low voltage cables shall be properly layout and terminated on the Terminal block and fuse box assembly inside the hand hole of the lighting pole. Complete the grounding and bonding of grounding cables including armor of power cable. Provide listed terminal lugs all cables and including internal wiring connections. Raise RFI for visual inspections. Use heat shrinkable sleeves for cable/core for identification. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-04 |  | Project Specifications Section 16120/16999, Scope of Work Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-0 |  | From STA 4+150 to STA 9+000 |  | 266 | N | CLOSED | 42920
267 | P | Complete the installation and testing of copper-jacketed grounding rod for all lighting poles. Raise RFI for visual inspections. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-04 |  | SAES-P-111, Project Specifications Section 16450, SOW Phase 700, SATIP-P-111-001, Standard drawing # AB-036398-001-01 & IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 | 1 | 267 | N | CLOSED | 42920
268 | P | After testing of power cables, perform final tightening of cables and wires connections to terminal block and fuse box assembly. Raise RFI for visual inspections. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-04 |  | SAES-P-104 para. 4.1, Project Specifications Section 16120/16999, SOW Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 | 1 | 268 | N | CLOSED | 42920
269 | P | Sealed the PVC conduits with approved and UL listed sealing compound for all incoming/outgoing cables of lighting pole concrete foundations prior to placement of sand covering, red concrete tiles and yellow warning tapes. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | SAES-P-104 para. 4.1, SAES-P-111, Project Specifications Section 16120/16999/16450/16550, SOW Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms. |  | From STA 4+150 to STA 9+000 |  | 269 | N | CLOSED | 42919
270 | P | Provide cable and wire identification at the termination block & fuse box assembly and lighting fixtures. Raise RFI for visual inspections. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-104 para. 6.10 & Project Specifications Section 16120 |  | From STA 4+150 to STA 9+000 |  | 270 | N | OPEN
271 | P | Two (2) meters around the lighting pole foundation that are backfilled without placement of sand bedding, sand covering, red concrete tiles and yellow warning tapes. NOTE: Inform PID for visual inspection of all installed cables prior to placement of sand covering, red concrete tile and warning tapes. Failure to comply the EIL item will not be close. | N | 2015-10-10 | Damian | PID | CLOSED | 2017-07-03 |  | Contractor internal NCR # 48, Project Specifications Section 16120, SOW Phase 700, SATIP-104-01, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 271 | N | CLOSED | 42919
272 | P | Perform illumination test. Test results shall meet the minimum illumination level as specified in SAES-P-123. Test instrument used for testing shall be calibrated and provide calibration test certificate from the approved third party agency. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16999 para. 3.04 and SAES-P-123 para. 5, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 272 | N | OPEN
273 | P | Provide the lighting pole tag number using nameplates and engraved on a three-layer 2 traffolyte plate having minimum thickness of 2 mm and have black letters on white background as per IFC drawings. Use approved adhessive compound materials suitable for fixing on the hot dipped galvanized lighting pole. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16999 para. 3.04 and SAES-P-123 para. 5, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 4+150 to STA 9+000 |  | 273 | N | OPEN
274 | P | Prior to grouting of concrete foundations, Check the horizontal and vertical alignment of all installed lighting pole assembly. Submit the visual inspection of concrete foundations from civil and approved survey reports by Saudi Aramco surveyor. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 274 | N | OPEN
275 | P | Mounting of base plate on the foundation shall complete with nuts and plain round washers both top and bottom of the base plate | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 275 | N | OPEN
276 | P | Hand hole cover are properly tight and close and replace or repair rubber gasket | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 276 | N | OPEN
277 | P | Repair any damage coating as per manufacturer's recommendations. All Anchor bolts thread shall be exposed minimum to a minimum of 2-3 threads. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123-001 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 277 | N | OPEN
278 | P | Complete the installation of remaining road lightings with hot dipped galvanized lighting pole, HID lighting fixture, 3C x 4 mm2 CU/XLPE/PVC multi-core cable, terminal block and fuse box assembly, stainless steel bolts SS 304 and including all accessories as per IFC drawings and approved shop drawings. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16550, Scope of Work, Phase 700 para. 3.4.5. & SATIP-P-123, SAES-P-104 and NEC Section 110.12, IFC dwg # VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 | 1 | 278 | N | OPEN
279 | P | Replace the galvanized bolts for all installed hot dipped galvanized lighting poles with stainless steel SS 304 materials suitable for severe corrosive area of all lighting pole arm assembly. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-100 Section 9, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 279 | N | OPEN
280 | P | Replace the existing installed LV cables (power cables) which are being cut near the lighting pole with new cables. Perform thermite welding of below grade connections of copper-jacketed grounding rods and grounding cables. Raise RFI for material receiving inspections of molds, powder and raise RFI for thermite weld connections. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-100, SAES-P-104, SAES-P-111, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 | 1 | 280 | N | OPEN
281 | P | Peform termite welding between ground rod and grounding cable for all llight poles and Provide bituminous paint, rubber and PVC electrical tape after thermite welding.Raise RFI for sand bedding, cable installation, placement of sand covering, red tiles and yellow warning tapes. NOTE: splicing of power cable (power circuit) is not acceptable except for grounding cable. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-100, SAES-P-104, SAES-P-111, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 | 1 | 281 | N | OPEN
282 | P | Perform continuity for power cable, equipment grounding conductors (EGC), Steel Wire Armour (SWA) of power cable and insulation resistance test of low voltage power cables for all road lightings. Ensure individual continuity test are being perform for all equipment grounding conductors (EGC) and Steel Wire Armour (SWA) of power cable. Use calibrated test instruments. Raise RFI for testing of cables. Records all the test results in the Saudi Aramco pre-commissioning forms. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16120/16999, Scope of Work Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 | 1 | 282 | N | OPEN
283 | P | For all road lightings, Low voltage cables shall be properly layout and terminated on the Terminal block and fuse box assembly inside the hand hole of the lighting pole. Complete the grounding and bonding of grounding cables including armor of power cable. Provide listed terminal lugs all cables and including internal wiring connections. Raise RFI for visual inspections. Use heat shrinkable sleeves for cable/core for identification. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16120/16999, Scope of Work Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-0 |  | From STA 9+000 to STA 14+460 | 1 | 283 | N | OPEN
284 | P | Complete the installation and testing of copper-jacketed grounding rod for all lighting poles. Raise RFI for visual inspections. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-111, Project Specifications Section 16450, SOW Phase 700, SATIP-P-111-001, Standard drawing # AB-036398-001-01 & IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 | 1 | 284 | N | OPEN
285 | P | After testing of power cables, perform final tightening of cables and wires connections to terminal block and fuse box assembly. Raise RFI for visual inspections. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-104 para. 4.1, Project Specifications Section 16120/16999, SOW Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 | 1 | 285 | N | OPEN
286 | P | Sealed the PVC conduits with approved and UL listed sealing compound for all incoming/outgoing cables of lighting pole concrete foundations prior to placement of sand covering, red concrete tiles and yellow warning tapes. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-104 para. 4.1, SAES-P-111, Project Specifications Section 16120/16999/16450/16550, SOW Phase 700 para. 3.4.5, SATIP-104-01. & SATIP-P-123-001. Pre-commissioning test forms. |  | From STA 9+000 to STA 14+460 |  | 286 | N | OPEN
287 | P | Provide cable and wire identification at the termination block & fuse box assembly and lighting fixtures. Raise RFI for visual inspections. | N | 2015-10-10 | Damian | PID | OPEN |  |  | SAES-P-104 para. 6.10 & Project Specifications Section 16120 |  | From STA 9+000 to STA 14+460 |  | 287 | N | OPEN
288 | P | Two (2) meters around the lighting pole foundation that are backfilled without placement of sand bedding, sand covering, red concrete tiles and yellow warning tapes. NOTE: Inform PID for visual inspection of all installed cables prior to placement of sand covering, red concrete tile and warning tapes. Failure to comply the EIL item will not be close. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Contractor internal NCR # 48, Project Specifications Section 16120, SOW Phase 700, SATIP-104-01, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 288 | N | OPEN
289 | P | Perform illumination test. Test results shall meet the minimum illumination level as specified in SAES-P-123. Test instrument used for testing shall be calibrated and provide calibration test certificate from the approved third party agency. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16999 para. 3.04 and SAES-P-123 para. 5, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 289 | N | OPEN
290 | P | Provide the lighting pole tag number using nameplates and engraved on a three-layer 2 traffolyte plate having minimum thickness of 2 mm and have black letters on white background as per IFC drawings. Use approved adhessive compound materials suitable for fixing on the hot dipped galvanized lighting pole. | N | 2015-10-10 | Damian | PID | OPEN |  |  | Project Specifications Section 16999 para. 3.04 and SAES-P-123 para. 5, IFC dwg # VA-846517-005-0F1/VA-846517-006-0F2/VA-846517-007-0F1/VA-846517-008-0F1/VA-846517-009-0F1/VA-846517-005-0F1/VA-846492-009-00/IC-SD-846492-201-00 |  | From STA 9+000 to STA 14+460 |  | 290 | N | OPEN
291 | Q | Complete the installation of 50mm thick Asphalt wearing coarse and its components for patrol road in Dike#2 in Retaining wall#8 from Sta.0+835.7 to 0+891 as per IFC drawing and follow typical inspection plan. | N | 2015-10-10 | MRS | PID | OPEN |  |  | refer to email dated December 1, 2015 EIL item # 575 |  | Interface between Wadi Khulais and Flood Control Chanel Project | 1 | 291 | N | OPEN
292 | Q | Complete the installation of 50mm thick Asphalt wearing coarse and its components for patrol road in Dike#2 from Sta.0+891 to end of dike as per IFC drawing and follow typical inspection plan. | N | 2015-10-10 | MRS | PID | OPEN |  |  | refer to email dated December 1, 2015 EIL item # 576 |  | Interface between Wadi Khulais and Flood Control Chanel Project | 1 | 292 | N | OPEN
293 | Q | Complete the installation of 50mm thick Asphalt wearing coarse and its components for patrol road in Dike#1 from Sta.2+102 to end of dike as per IFC drawing and follow typical inspection plan. | N | 2015-10-10 | MRS | PID | OPEN |  |  | refer to email dated December 1, 2015 EIL item # 581 |  | Interface between Wadi Khulais and Flood Control Chanel Project | 1 | 293 | N | OPEN
294 | Q | Complete the Patrol Road that is accessible going to the Culvert #2 | N | 2015-10-10 | MRS | PID | OPEN |  |  | refer to email dated December 1, 2015 EIL item # 609 |  | Interface between Wadi Khulais and Flood Control Chanel Project | 1 | 294 | N | OPEN